## Sheet1
Always-On TODO List - Version of Oct 10, 2013
alpha = protype works w. known deficiencies
| Note: Days are to final fieldable status |  |  |  | beta = all functionality present, but may have bugs
| Task | Person-Days |  | Who | Status | Description
|  | (optimistic) | (pessimistic)
Disco-Based (Purely
Conversational) Plugins
| Greetings | 1 | 2 | WPI:Sidner | Beta | Very small, needs evening
| About | 2 | 4 | WPI:Sidner | Beta | Needs testing and polishing
| Explain | 3 | 5 | WPI:Sidner | Alpha | Not complete coverage yet
| Weather | 8 | 14 | WPI:Behrooz | Alpha | Backend needs to be made more robust
Plugins with GUI's
| Enroll | 3 | 5 | WPI:Behrooz | Beta | Needs testing
| TTT | 1 | 1 | WPI:Behrooz | Beta | Needs better language content
| Calendar | 2 | 4 | WPI:Behrooz | Beta | Needs testing
| Rummy | 5 | 10 | WPI:Behrooz | Alpha | Needs work and language content
| Skype | 10 | 20 | NEU:Ring | Alpha | Currently stand-alone only
| Story | 20 | 30 | NEU:Ring | Dev | Recording/playback, vimeo, initiation
Legacy Plugins
| Scriptbuilder | 5 | 10 | NEU:Ring | Alpha | framework, Initial integration, has some bugs
| Anecdotes | 3 | 10 | NEU:Zessie | Alpha | Scripts
| Exercise | 3 | 10 | NEU:Zessie | Alpha | Scripts
| Nutrition | 3 | 10 | NEU:Zessie | Alpha | Scripts
| Health Tips | 6 | 20 | Neu:Zessie | Dev | Scripts
General
| Unity Client | 5 | 10 | NEU:Ring | Beta | Has bugs and needs artistic improvements
| Session Manager | 5 | 12 | WPI:Rich | Alpha | Interruptions, clock events
| Engagement Manager | 5 | 10 | WPI:Shayganfar | Dev | Needs motion detector
|  | 3 | 6 | WPI:Rich | Dev
| Logging | 2 | 4 | WPI:Rich | Design | For QA and research results
|  | 2 | 4 | NEU:Ring | Design | .Net side
| Quality Assurance | 15 | 20 | NEU:Writer | Design | Evaluate scripts
|  | 15 | 20 | WPI:Sidner | Design | Checking all utterances w TTS, etc.
| Build/Release | 5 | 8 | WPI:Rich | Design | Direct build from Git; DropBox
| Windows Harden | 3 | 5 | NEU:Ring | Design | Hide WIndows; nightly reboot
Reeti
| Face Tracking | 3 | 5 | WPI:Shayganfar | Alpha | Works well horizontally, adding vertical
| Facial Expressions | 3 | 6 | WPI:Shayganfar | Dev | Fairly small job
TOTAL DAYS |  | 141 | 265
(22 person-days = 1 person-month, assuming doing nothing else!)
| WPI: Rich | 15 | 30
| WPI:Sidner | 21 | 31
| WPI:Behrooz | 19 | 34
| WPI:Shayganfar | 11 | 21
| NEU:Ring | 45 | 79
| NEU:Zessie | 15 | 50
| NEU:Writer | 15 | 20
|  | 141 | 265