## Sheet1
Always-On TODO List - Version of Oct 16, 2013
alpha = protype works w. known deficiencies
| Note: Days are to final fieldable status |  |  |  | beta = all functionality present, but may have bugs
| Task | Person-Days |  | Who | Status | Description
|  | (optimistic) | (pessimistic)
Disco-Based (Purely
Conversational) Plugins
| Greetings | 1 | 2 | WPI:Sidner | Beta | Very small, needs evening
| About | 2 | 4 | WPI:Sidner | Beta | Needs testing and polishing
| Explain | 3 | 5 | WPI:Sidner | Alpha | Not complete coverage yet
| Weather | 8 | 14 | WPI:Behrooz | Alpha | Backend needs to be made more robust
Plugins with GUI's
| Enroll | 3 | 5 | WPI:Behrooz | Beta | Needs testing
| TTT | 1 | 1 | WPI:Behrooz | Beta | Needs better language content
| Calendar | 2 | 4 | WPI:Behrooz | Beta | Needs testing
| Rummy | 5 | 10 | WPI:Behrooz | Alpha | Needs work and language content
| Skype | 10 | 20 | NEU:Ring | Alpha | Currently stand-alone only. AFTER CAMERA CONTROL AND INTERRUPT HANDLING WORKS.
| Story | 10 | 20 | NEU:Ring | Dev | Recording/playback, vimeo, initiation (10 for basic stand-alone recording). AFTER SKYPE WORKS
Legacy Plugins
| Scriptbuilder | 2 | 5 | NEU:Ring | Alpha | framework, Initial integration, has some bugs
| Anecdotes | 1 | 3 | NEU:Zessie | Alpha | Scripts
| Exercise | 3 | 5 | NEU:Zessie | Alpha | Scripts
| Nutrition | 3 | 10 | NEU:Zessie | Alpha | Scripts
| Health Tips | 2 | 4 | Neu:Zessie | Dev | Scripts
General
| Unity Client | 5 | 10 | NEU:Ring | Beta | Has bugs and needs artistic improvements
| Session Manager | 5 | 12 | WPI:Rich | Alpha | Interruptions, clock events
| Engagement Manager | 5 | 10 | WPI:Shayganfar | Dev | Needs motion detector
|  | 3 | 6 | WPI:Rich | Dev
| Logging | 2 | 4 | WPI:Rich | Design | For QA and research results
|  | 2 | 4 | NEU:Ring | Design | .Net side
| Quality Assurance | 15 | 20 | NEU:Writer | Design | Evaluate scripts
|  | 15 | 20 | WPI:Sidner | Design | Checking all utterances w TTS, etc.
| Build/Release | 5 | 8 | WPI:Rich | Design | Direct build from Git; DropBox
| Windows Harden | 1 | 5 | NEU:Yin | Design | Hide WIndows; nightly reboot
Reeti
| Face Tracking | 0 | 0 | WPI:Shayganfar | Beta | Works well horizontally, adding vertical | done
| Facial Expressions | 3 | 6 | WPI:Shayganfar | Dev | Fairly small job
TOTAL DAYS |  | 117 | 217
(22 person-days = 1 person-month, assuming doing nothing else!)
| WPI: Rich | 15 | 30
| WPI:Sidner | 21 | 31
| WPI:Behrooz | 19 | 34
| WPI:Shayganfar | 8 | 16
| NEU:Ring | 29 | 59
| NEU:Zessie | 9 | 22
| NEU:Writer | 15 | 20
| NEU:Yin | 1 | 5
|  | 117 | 217
Total hours |  |  |  | Total weeks*2 days/wk
| WPI: Rich | 120 | 240 | 7.5 | 15
| WPI: Sidner | 168 | 248 | 10.5 | 15.5
| WPI: Behrooz | 152 | 272 | 9.5 | 17
| WPI: Shayganfar | 64 | 128 | 4 | 8
| NEU: Ring | 232 | 472 | 14.5 | 29.5
| NEU: Zessie | 72 | 176 | 4.5 | 11
| NEU: Writer | 120 | 160 | 7.5 | 10
| NEU: Yin | 8 | 40 | 0.5 | 2.5